## Project Inputs
BURN DOWN CHART
Sprint 1 User Stories
US-1.1 (13 hrs) – Scope & Success Criteria
US-1.2 (13 hrs) – Architecture & Diagrams
US-1.3 (8 hrs) – Backlog & MoSCoW
Total Sprint Effort = 34 hours
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Actual Efforts ( Hours) | 34 | 30 | 23 | 15 | 6 | 0
Ideal Effort (Hours) | 34 | 27.2 | 20.4 | 14 | 7.2 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Total
Define Scope & Success Criteria | 13 | 4 | 4 | 3 | 2 | 0 | 13
Create Architecture/Class Diagrams | 13 | 3 | 5 | 3 | 1 | 1 | 13
Backlog + MoSCoW Prioritization | 8 | 1 | 2 | 2 | 1 | 2 | 8