## Project Inputs
BURN DOWN CHART
Sprint 2 User Stories
US-2.1 (13 hrs) – AI Budget Design
US-2.2 (13 hrs) – Automated Allocation
US-2.3 (8 hrs) – Real-Time Dashboard
Total Sprint Effort = 34 hours
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Actual Efforts ( Hours) | 34 | 30 | 24 | 16 | 8 | 0
Ideal Effort (Hours) | 34 | 27.2 | 20.4 | 14 | 7.2 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Total
Implement Budget Design Agent | 13 | 3 | 4 | 3 | 2 | 1 | 13
Implement Budget Allocation Service | 13 | 2 | 4 | 4 | 2 | 1 | 13
Real-Time Dashboard Integration | 8 | 2 | 2 | 3 | 1 | 0 | 8