## Project Inputs
BURN DOWN CHART
Sprint 3 User Stories
US-3.1 (13 hrs) – Signup/Login Flow
US-3.2 (13 hrs) – Logout + Session Handling
US-3.3 (8 hrs) – Validation + Security Checks
Total Sprint Effort = 34 hours
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Actual Efforts ( Hours) | 34 | 28 | 21 | 13 | 6 | 0
Ideal Effort (Hours) | 34 | 27.2 | 20.4 | 14 | 7.2 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Total
Implement Signup/Login | 13 | 4 | 4 | 3 | 1 | 1 | 13
Implement Logout/Session | 13 | 2 | 5 | 3 | 2 | 1 | 13
Validation + Security Checks | 8 | 0 | 2 | 2 | 3 | 1 | 8