## Project Inputs
BURN DOWN CHART
Sprint 4 User Stories
US-4.1 (13 hrs) – JWT Token Auth
US-4.2 (13 hrs) – Security Policies
US-4.3 (8 hrs) – Role-Based Access (Basic)
Total Sprint Effort = 34 hours
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Actual Efforts ( Hours) | 34 | 31 | 25 | 18 | 9 | 0
Ideal Effort (Hours) | 34 | 27.2 | 20.4 | 14 | 7.2 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Total
JWT Token Authentication | 13 | 3 | 4 | 3 | 2 | 1 | 13
Security Policies (rate limit/validation) | 13 | 2 | 4 | 4 | 2 | 1 | 13
Role-based Access Control | 8 | 1 | 2 | 0 | 3 | 2 | 8