## Project Inputs
BURN DOWN CHART
Sprint 5 User Stories
US-5.1 (13 hrs) – Expense CRUD APIs
US-5.2 (13 hrs) – DB Connection + Schema
US-5.3 (8 hrs) – Routing + Error Handling
Total Sprint Effort = 34 hours
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Actual Efforts ( Hours) | 34 | 29 | 22 | 15 | 7 | 0
Ideal Effort (Hours) | 34 | 27.2 | 20.4 | 14 | 7.2 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Total
Expense CRUD APIs | 13 | 4 | 4 | 3 | 2 | 0 | 13
DB Connection + Schema | 13 | 3 | 4 | 4 | 1 | 1 | 13
Routing + Error Handling | 8 | 2 | 0 | 2 | 2 | 2 | 8