## Project Inputs
BURN DOWN CHART
Sprint 6 User Stories
US-6.1 (13 hrs) – Dashboard Layout
US-6.2 (13 hrs) – Expense Entry Screens + API Integration
US-6.3 (8 hrs) – Charts + Filtering
Total Sprint Effort = 34 hours
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Actual Efforts ( Hours) | 34 | 30 | 23 | 17 | 10 | 0
Ideal Effort (Hours) | 34 | 27.2 | 20.4 | 14 | 7.2 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Total
Dashboard Layout & Navigation | 13 | 4 | 3 | 3 | 2 | 1 | 13
Expense Entry UI + API Integration | 13 | 3 | 4 | 3 | 2 | 1 | 13
Charts + Filtering | 8 | 0 | 2 | 1 | 3 | 2 | 8