## Project Inputs
BURN DOWN CHART
Sprint 7 User Stories
US-7.1 (13 hrs) – Expense Categorization AI
US-7.2 (13 hrs) – Budget Prediction Baseline
US-7.3 (8 hrs) – AI Integration Pipeline
Total Sprint Effort = 34 hours
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Actual Efforts ( Hours) | 34 | 32 | 26 | 19 | 11 | 0
Ideal Effort (Hours) | 34 | 27.2 | 20.4 | 14 | 7.2 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Total
Expense Categorization Model | 13 | 3 | 4 | 3 | 2 | 1 | 13
Budget Prediction Baseline | 13 | 2 | 4 | 4 | 2 | 1 | 13
AI Integration Pipeline | 8 | 0 | 2 | 2 | 2 | 2 | 8