## Project Inputs
BURN DOWN CHART
Sprint 8 User Stories
US-8.1 (13 hrs) – Backend Unit Testing
US-8.2 (13 hrs) – UI Testing + Bug Fixes
US-8.3 (8 hrs) – Feature Verification
Total Sprint Effort = 34 hours
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Actual Efforts ( Hours) | 34 | 31 | 23 | 16 | 8 | 0
Ideal Effort (Hours) | 34 | 27.2 | 20.4 | 14 | 7.2 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Total
Backend Unit Testing | 13 | 3 | 4 | 3 | 2 | 1 | 13
UI Testing + Bug Fixes | 13 | 2 | 4 | 4 | 2 | 1 | 13
Feature Verification Checklist | 8 | 0 | 2 | 0 | 4 | 2 | 8