## Project Inputs
BURN DOWN CHART
User Stories
US (13 hrs) – Deployment Plan + Setup Guide
US (13 hrs) – Demo Prep + Final Polish
US (8 hrs) – Sprint Review + Documentation Pack
Total Sprint Effort = 34 hours
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Actual Efforts ( Hours) | 34 | 30 | 22 | 14 | 6 | 0
Ideal Effort (Hours) | 34 | 27.2 | 20.4 | 14 | 7.2 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Total
Deployment Plan + Setup Guide | 13 | 4 | 4 | 3 | 1 | 1 | 13
Demo Prep + Final Polish | 13 | 2 | 4 | 4 | 2 | 1 | 13
Sprint Review + Documentation Pack | 8 | 2 | 0 | 1 | 3 | 2 | 8